## Sheet1
Sub Problem | Developer | 16th March | 19th March | 23rd March | 26th March | 30th March | 2nd April | 6th April | 9th April
Read Data File | Helga | All info can be accessed by loop | Complete
Hashmap/Class | Precious/ Jennifer | CVS info can be stored | Complete
Graphic Visuals | Maria | Writing code in progress | Data can be accesses and placed in graphs | Complete
User Interface | Keelin | Layout | Pages designed | Buttons working | Navigation | Data/graphs can be accesses | Additional features
Filtering |  |  |  |  | Complete